## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
18 | As a potential user, I want to be able to access Poppin through a homepage, so that I can see all of the features in one place. | 1) Design the homepage UI(1/3), 2) Illustrate site graphics(1/3), 3) Code the User Interface(1/2), 4) Code buttons with funcional hyperlinks(1/2), 5)Test interactive buttons(1/3) | 2 | Tasks 4 and 5 | F - T | 2 | 5/6 (Tasks 4, 5) | Brett P: Tasks 4, 5 (100%)
5 | As a movie-loving user who enjoys rating movies, I want to be able to include a 0-10 rating on each post so that I can indicate how I feel about each movie I watch with a numerical rating. | 1)Code to allow the user to enter a number for the rating(1/2). 2)Code to check if the rating is between 1 and 10 (1/2). 3)Code to validate the user input.1/2) 4) Code to display the user input(1/2) | 2 | Tasks 1 and 2 | F - T | 2 | 2 (Tasks 1, 2 3, 4) | Emmanuelle: Tasks 1,2,3,4 (100%), Emmanuelle: 34% of use case document
6 | As a book-loving user who best describes things with words, I want to be able to include a caption with each post so that I can verbally express how I feel about the books I read. | 1)Code to allow the user to enter text(1). 2)Code to validate the user input(1/2). 3) Code to display the user input (1/2) | 2 | Tasks 1 2 and 3 | F - T | 2 | 2 | Wesley & Emmanuelle: Task 1,2,3(100%)
3 | As a video game-loving user, I want to be able to post pictures of the games that I play so that my followers can keep up to date with the video games I play. | 1) Code to allow user to upload images (1/2) 2) Code to display the uploaded images (1/2) 3) Code to connect Posts with account (1/2) 4) Test that users can sucessfully create posts (1/2) | 2 | Tasks 1 and 2 | F - T | 2 | 1 (Tasks 1, 2) | Wesley: Tasks 1, 2 (100%) Wesley: 33% of the Use Case Document
1 | As an unregistered user, I want to be able to create an account with a username and password so that I can securely access the full features of Poppin. | 1) Code the UI for registration (1/2) 2) Code the database for registration information(1) 3)Code interactions between the register page and database(1). 4) Test that users can register with a username and password(1/2) | 2 | Tasks 1, 2 | F - T | 3 | 1 1/2 (Tasks 1,2) | Brett P: Tasks 1, 2 (100%) Brett P: 50% of architecture document, 33% of use case model
2 | As a registered user, I want to be able to log in with a username and password so that I can use Poppin’s features from my specific account. | 1) Code the Login Page UI (1/2) 2)Code interaction with register database(1/2) 3) Code for login credentials to be saved (1/2) 4)Test that users can login with registered username and password (1/2) | 2 | Tasks 1 and 2 | F - T | 2 | 1 (Tasks 1,2) | Monica: Tasks 1, 2 (100%) Monica: 50% of architecture document