## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
3 | As a video game-loving user, I want to be able to post pictures of the games that I play so that my followers can keep up to date with the video games I play. | 1) Code to allow user to upload images (1/2) 2) Code to display the uploaded images (1/2) 3) Code upload text components of Posts to Database (1/4) 4) Have a default image for posts 5) Code to upload Post Images to Database (1/4) 6) Test that users can sucessfully create posts (1/4) | 4 | Task 4 | F - T | 2 | 2024-01-04 | Wesley Dumas - 100%
13 | As a shy user, I want to tap a thumbs up emoji to like a post, so that I can acknowledge that I enjoy someone’s content without writing a personal message. | 1) Code the UI for the like button (1/2) 2) Code for user to be able to like the post (1/2) 3) Code to store that the user has liked (1/2) 4) Test that users can sucessfully like posts (1/2) | 4 | Tasks 3, 4 | F - T | 2 | 1 | Wesley Dumas - 100%
14 | As a social user, I want to be able to interact with posts by leaving comments, so that I can engage in discussions with other users about their content. | 1) Code to allow users to input and display their comments (1/2) 2) Code to attach comments in each post (1/2) 3)Code to allow user to delete or reply to comments (1/2) 4)Code post to have a comment attribute in datatbase (1) 5) Code to attach each comments with its user (1/2) | 4 | Tasks 4 | F-T | 3 | 1 | Emmanuelle - 100%
7 | As a user who likes interacting with friends, I want to be able to follow my friends via a username so that I can see what media my friends are consuming. | 1) Code to allow users to display the follow/unfollow button(1) 2) Code to attach the follow button in each post (1) 3)Code to save the follow in the database (1) | 4 | Tasks 1,2 | F-T | 3 | 2 | Emmanuelle - 100%
9 | As a user who wants to gain followers, I want to be able to have a public profile that showcases my interests so that I can attract people with similar interests to follow me. | 1) Code the UI of what a user's own profile would look like(1) 2) Code the UI of what another user's profile would look like (1) 3) Connect profiles to the database (2) | 4 | Task 1 | F - T | 4 | 1 | Brett - 100%
11 | As a gamer who loves Fortnite, I want to be able to have a “favorite video game” feature on my profile so that I can showcase my favorite game to my followers. | 1) Code retrieval of user's created posts(1) 2) Code for the selected post to be rendered and displayed in respective box(1) 3)Code UI of post selection and format four featured posts(1) | 4 | Tasks 1,3 | F-T | 3 | 2 | Monica - 100%
15 | As a registered user, I want to be able to create a short bio so that other people visiting my page can learn more about me. | 1) Add bio as an attribute to user (1/2) 2) Allow a user to edit their bio on their profile (1) 3) Display the user's changes to bio (1/2) | 4 | Task 1 | F-T | 2 | 2024-01-02 | Brett - 100%