## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
19 | As a user, I want "Poppin" to be written on the tab for the page, so I know which tab is Poppin if I have multiple tabs open. | 1 | L | D | 1
18 | As a potential user, I want to be able to access Poppin through a homepage, so that I can see all of the features in one place. | 1 +2 | H | D | 2
1 | As an unregistered user, I want to be able to create an account with a username and password so that I can securely access the full features of Poppin. | 2+3 | H | D | 3
2 | As a registered user, I want to be able to log in with a username and password so that I can use Poppin’s features from my specific account. | 2+3 | H | D | 2
3 | As a video game-loving user, I want to be able to post pictures of the games that I play so that my followers can keep up to date with the video games I play. | 2+3 | H | IP | 2
5 | As a movie-loving user who enjoys rating movies, I want to be able to include a 0-10 rating on each post so that I can indicate how I feel about each movie I watch with a numerical rating. | 2 | M | D | 2
6 | As a book-loving user who best describes things with words, I want to be able to include a caption with each post so that I can verbally express how I feel about the books I read. | 2 | M | D | 2
4 | As a music-loving user, I want to attach a “Music” tag to my post so that it is seen by other users who specifically want music related content. | 3 | M | D | 2
13 | As a shy user, I want to tap a thumbs up emoji to like a post, so that I can acknowledge that I enjoy someone’s content without writing a personal message. | 3 | M | IP | 2
14 | As a social user, I want to be able to interact with posts by leaving comments, so that I can engage in discussions with other users about their content. | 3 | M | IP | 3
7 | As a user who likes interacting with friends, I want to be able to follow my friends via a username so that I can see what media my friends are consuming. | 4 | L | W | 3
9 | As a user who wants to gain followers, I want to be able to have a public profile that showcases my interests so that I can attract people with similar interests to follow me. | 4 | M | W | 4
11 | As a gamer who loves Fortnite, I want to be able to have a “favorite video game” feature on my profile so that I can showcase my favorite game to my followers. | 4 | M | W | 3
15 | As a registered user, I want to be able to create a short bio so that other people visiting my page can learn more about me. | 4 | L | W | 2
8 | As a music-loving user, I want to be able to filter my feed with a “Music” tag so that I can look at content specific to music. | 5 | L | W | 3
10 | As a user who prefers a small circle of friends, I want the ability to make my profile private so that only people I approve of can see the media that I consume. | 5 | L | W | 3
12 | As a registered user, I want to explore trends by accessing the "Trending" section on top of the app, so that I can find popular trends that interest me. | 5 | L | W | 8
16 | As a user who likes to partake in civil discussion, I want to be able to block users who post negative or harmful content, so that I can have a comfortable experience with Poppin. | 5 | L | W | 5
17 | As a user only interested in books, I want to be able to filter other people’s profiles by books, so I can exclusively see their posts about books. | 5 | L | W | 4