## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
3 | As a video game-loving user, I want to be able to post pictures of the games that I play so that my followers can keep up to date with the video games I play. | 1) Code to allow user to upload images (1/2) 2) Code to display the uploaded images (1/2) 3) Code upload text components of Posts to Database (1/4) 4) Code to upload Post Images to Database (1/4) 5) Test that users can sucessfully create posts (1/2) | 3 | Tasks 3 | F - T | 2 | 2024-01-04 | Wesley - 100%
1 | As an unregistered user, I want to be able to create an account with a username and password so that I can securely access the full features of Poppin. | 1) Code the UI for registration (1/2) 2) Code the database for registration information(1) 3)Code interactions between the register page and database(1). 4) Test that users can register with a username and password(1/2) | 3 | Tasks 3 and 4 | F - T | 3 | 1 1/2 | Brett - 100%
2 | As a registered user, I want to be able to log in with a username and password so that I can use Poppin’s features from my specific account. | 1) Code the Login Page UI (1/2) 2)Code interaction with register database(1/2) 3) Code for login credentials to be saved (1/2) 4)Test that users can login with registered username and password (1/2) | 3 | Tasks 3 and 4 | F - T | 2 | 1 | Brett - 100%
13 | As a shy user, I want to tap a thumbs up emoji to like a post, so that I can acknowledge that I enjoy someone’s content without writing a personal message. | 1) Code the UI for the like button (1/2) 2) Code for user to be able to like the post (1/2) 3) Code to store that the user has liked (1/2) 4) Test that users can sucessfully like posts (1/2) | 3 | Tasks 1, 2 | F - T | 2 | 1 | Wesley - 100%
4 | As a music-loving user, I want to attach a “Music” tag to my post so that it is seen by other users who specifically want music related content. | 1) Code the button to choose a tag from the options (2/3) 2) Code tag attachment to post (2/3) 3) Code Post to have a tag attribute in database (2/3) | 3 | Tasks 1,2,3 | F - T | 2 | 2 | Monica - 100%
14 | As a social user, I want to be able to interact with posts by leaving comments, so that I can engage in discussions with other users about their content. | 1) Code to allow users to input and display their comments (1/2) 2) Code to attach comments in each post (1/2) 3)Code to allow user to delete or reply to comments (1) 4)Code post to have a comment attribute in datatbase (1) | 3 | Tasks 1,2,3 | F-T | 3 | 2 | Emmanuelle -100%